## Shutdown Calendar
plant_id | shutdown_id | shutdown_name | shutdown_type | planned_start | planned_end | planned_hours | areas_csv | description | status
OCP-CON1 | SD-2026-01-MIN | Parada Menor Enero Molienda | MINOR_8H | 2026-01-15 | 2026-01-15 | 8 | Molienda | Inspeccion rapida revestimientos SAG | PLANNED
OCP-CON1 | SD-2026-01-PM | Parada Programada Enero Chancado | MINOR_12H | 2026-01-28 | 2026-01-28 | 12 | Chancado | Cambio mallas harneros e inspeccion correas | PLANNED
OCP-CON1 | SD-2026-02-MAJ | Parada Mayor Febrero Planta | MAJOR_72H | 2026-02-10 | 2026-02-13 | 72 | Chancado,Molienda,Flotacion,Espesado,Filtrado | Overhaul semestral planta concentradora | PLANNED
OCP-CON1 | SD-2026-03-MIN | Parada Menor Marzo Flotacion | MINOR_8H | 2026-03-12 | 2026-03-12 | 8 | Flotacion | Cambio rotores celdas rougher | PLANNED
OCP-CON1 | SD-2026-03-PM | Parada Programada Marzo Filtrado | MINOR_12H | 2026-03-25 | 2026-03-25 | 12 | Filtrado | Cambio telas filtrantes FP-01 | PLANNED
OCP-CON1 | SD-2026-04-MIN | Parada Menor Abril Chancado | MINOR_8H | 2026-04-09 | 2026-04-09 | 8 | Chancado | Cambio mantos chancador secundario | PLANNED
OCP-CON1 | SD-2026-04-PM | Parada Programada Abril Espesado | MINOR_12H | 2026-04-22 | 2026-04-22 | 12 | Espesado | Inspeccion rastras espesador concentrado | PLANNED
OCP-CON1 | SD-2026-05-MAJ | Parada Mayor Mayo Molienda | MAJOR_48H | 2026-05-13 | 2026-05-15 | 48 | Molienda | Cambio revestimientos SAG y bolas, overhaul bombas | PLANNED
OCP-CON1 | SD-2026-06-MIN | Parada Menor Junio Flotacion | MINOR_8H | 2026-06-11 | 2026-06-11 | 8 | Flotacion | Inspeccion celdas cleaner-scavenger | PLANNED
OCP-CON1 | SD-2026-06-PM | Parada Programada Junio General | MINOR_12H | 2026-06-24 | 2026-06-24 | 12 | Chancado,Molienda | Inspeccion general area seca y molienda | PLANNED
OCP-CON1 | SD-2026-07-MIN | Parada Menor Julio Chancado | MINOR_8H | 2026-07-15 | 2026-07-15 | 8 | Chancado | Cambio mallas y ajuste chancador terciario | PLANNED
OCP-CON1 | SD-2026-08-MAJ | Parada Mayor Agosto Planta | MAJOR_72H | 2026-08-12 | 2026-08-15 | 72 | Chancado,Molienda,Flotacion,Espesado,Filtrado | Parada general semestral concentradora | PLANNED
OCP-CON1 | SD-2026-09-MIN | Parada Menor Sept Molienda | MINOR_8H | 2026-09-10 | 2026-09-10 | 8 | Molienda | Inspeccion GMD e hidrociclones | PLANNED
OCP-CON1 | SD-2026-09-PM | Parada Programada Sept Filtrado | MINOR_12H | 2026-09-23 | 2026-09-23 | 12 | Filtrado | Cambio placas y telas FP-02 | PLANNED
OCP-CON1 | SD-2026-10-MIN | Parada Menor Oct Espesado | MINOR_8H | 2026-10-08 | 2026-10-08 | 8 | Espesado | Mantencion espesador relaves | PLANNED
OCP-CON1 | SD-2026-11-MAJ | Parada Mayor Nov Molienda | MAJOR_48H | 2026-11-18 | 2026-11-20 | 48 | Molienda | Cambio revestimientos y overhaul completo | PLANNED
OCP-CON1 | SD-2026-12-MIN | Parada Menor Dic Flotacion | MINOR_8H | 2026-12-10 | 2026-12-10 | 8 | Flotacion | Inspeccion final ano celdas | PLANNED
OCP-CON1 | SD-2026-12-PM | Parada Programada Dic General | MINOR_12H | 2026-12-18 | 2026-12-18 | 12 | Chancado,Filtrado | Preparacion parada mayor Q1 2027 | PLANNED

## Shutdown Work Packages
shutdown_id | wp_code | equipment_tag | sap_func_loc | description | estimated_hours | work_center | specialty | crew_size | materials_required
SD-2026-01-MIN | WP-SD-2026-01-MIN-001 | OCP-CON1-CFSC01 | 02-03-02-CFSC01 | Trabajo parada: Celda Flotacion Scavenger 300m3 C1 | 9 | PAHINS01 | INS | 3 | Si
SD-2026-01-MIN | WP-SD-2026-01-MIN-002 | OCP-CON1-BAGP01 | 02-05-03-BAGP01 | Trabajo parada: Bomba Agua Proceso 01 | 4.4 | PASELE01 | INS | 3 | No
SD-2026-01-MIN | WP-SD-2026-01-MIN-003 | OCP-CON1-BREL01 | 02-04-02-BREL01 | Trabajo parada: Bomba Relaves 01 | 14.2 | PAHINS01 | ELE | 3 | No
SD-2026-01-MIN | WP-SD-2026-01-MIN-004 | OCP-CON1-MBOL03 | 02-02-02-MBOL03 | Trabajo parada: Molino Bolas 26x40.5 L3 | 13.7 | PARMEC01 | MEC | 4 | Si
SD-2026-01-MIN | WP-SD-2026-01-MIN-005 | OCP-CON1-COSE01 | 02-01-02-COSE01 | Trabajo parada: Chancador Cono Secundario HP800 L1 | 6.7 | PASMEC01 | INS | 2 | Si
SD-2026-01-MIN | WP-SD-2026-01-MIN-006 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 14.8 | PARMEC01 | ELE | 6 | No
SD-2026-01-MIN | WP-SD-2026-01-MIN-007 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 5.8 | PARELE01 | INS | 2 | Si
SD-2026-01-MIN | WP-SD-2026-01-MIN-008 | OCP-CON1-BOMB02 | 02-02-03-BOMB02 | Trabajo parada: Bomba Pulpa Descarga SAG 02 | 13.9 | PARMEC01 | ELE | 4 | Si
SD-2026-01-MIN | WP-SD-2026-01-MIN-009 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 13.1 | PAHELE01 | ELE | 2 | Si
SD-2026-01-PM | WP-SD-2026-01-PM-001 | OCP-CON1-CFCL01 | 02-03-02-CFCL01 | Trabajo parada: Celda Flotacion Cleaner 160m3 C1 | 15 | PAHINS01 | ELE | 2 | Si
SD-2026-01-PM | WP-SD-2026-01-PM-002 | OCP-CON1-ESPR01 | 02-04-02-ESPR01 | Trabajo parada: Espesador Relaves 45m | 14.7 | PAHINS01 | INS | 4 | Si
SD-2026-01-PM | WP-SD-2026-01-PM-003 | OCP-CON1-ESPC02 | 02-04-01-ESPC02 | Trabajo parada: Espesador Concentrado Hi-Rate 25m S | 6 | PAHELE01 | ELE | 2 | Si
SD-2026-01-PM | WP-SD-2026-01-PM-004 | OCP-CON1-BREL02 | 02-04-02-BREL02 | Trabajo parada: Bomba Relaves 02 StBy | 14.9 | PAHELE01 | MEC | 2 | No
SD-2026-01-PM | WP-SD-2026-01-PM-005 | OCP-CON1-VIBM01 | 02-05-03-VIBM01 | Trabajo parada: Monitor Vibracion Molinos | 6.6 | PASMEC01 | MEC | 6 | No
SD-2026-01-PM | WP-SD-2026-01-PM-006 | OCP-CON1-FILT01 | 02-05-01-FILT01 | Trabajo parada: Filtro Prensa Concentrado FP-01 | 15.4 | PASLUB01 | INS | 4 | No
SD-2026-01-PM | WP-SD-2026-01-PM-007 | OCP-CON1-FILT02 | 02-05-01-FILT02 | Trabajo parada: Filtro Prensa Concentrado FP-02 | 15 | PASINS01 | INS | 5 | No
SD-2026-01-PM | WP-SD-2026-01-PM-008 | OCP-CON1-CFRO03 | 02-03-01-CFRO03 | Trabajo parada: Celda Flotacion Rougher 300m3 C3 | 15.1 | PAHMEC01 | INS | 4 | Si
SD-2026-01-PM | WP-SD-2026-01-PM-009 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 3.4 | PASINS01 | MEC | 6 | No
SD-2026-01-PM | WP-SD-2026-01-PM-010 | OCP-CON1-DREA03 | 02-03-03-DREA03 | Trabajo parada: Dosificador Cal/pH | 15 | PAHELE01 | ELE | 4 | No
SD-2026-01-PM | WP-SD-2026-01-PM-011 | OCP-CON1-MBOL03 | 02-02-02-MBOL03 | Trabajo parada: Molino Bolas 26x40.5 L3 | 6.3 | PARELE01 | ELE | 4 | No
SD-2026-01-PM | WP-SD-2026-01-PM-012 | OCP-CON1-DENS01 | 02-05-03-DENS01 | Trabajo parada: Densimetro Nuclear Molienda | 13.4 | PASELE01 | INS | 5 | No
SD-2026-01-PM | WP-SD-2026-01-PM-013 | OCP-CON1-AGIT01 | 02-03-03-AGIT01 | Trabajo parada: Acondicionador Reactivos 01 | 10.9 | PAHELE01 | INS | 5 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-001 | OCP-CON1-CFCL02 | 02-03-02-CFCL02 | Trabajo parada: Celda Flotacion Cleaner 160m3 C2 | 6.9 | PAHMEC01 | INS | 3 | No
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-002 | OCP-CON1-ESPR01 | 02-04-02-ESPR01 | Trabajo parada: Espesador Relaves 45m | 12.3 | PAHINS01 | ELE | 4 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-003 | OCP-CON1-MBOL01 | 02-02-02-MBOL01 | Trabajo parada: Molino Bolas 26x40.5 L1 | 10.2 | PARINS01 | ELE | 4 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-004 | OCP-CON1-ESPC02 | 02-04-01-ESPC02 | Trabajo parada: Espesador Concentrado Hi-Rate 25m S | 7.2 | PAHELE01 | INS | 2 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-005 | OCP-CON1-BREL01 | 02-04-02-BREL01 | Trabajo parada: Bomba Relaves 01 | 6.3 | PAHELE01 | ELE | 6 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-006 | OCP-CON1-MBOL01 | 02-02-02-MBOL01 | Trabajo parada: Molino Bolas 26x40.5 L1 | 9.4 | PARINS01 | INS | 4 | No
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-007 | OCP-CON1-CFRO01 | 02-03-01-CFRO01 | Trabajo parada: Celda Flotacion Rougher 300m3 C1 | 4.7 | PAHMEC01 | MEC | 6 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-008 | OCP-CON1-DREA01 | 02-03-03-DREA01 | Trabajo parada: Dosificador Reactivos Colector | 3.5 | PAHELE01 | INS | 5 | No
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-009 | OCP-CON1-CFCL02 | 02-03-02-CFCL02 | Trabajo parada: Celda Flotacion Cleaner 160m3 C2 | 12.8 | PAHINS01 | MEC | 5 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-010 | OCP-CON1-BREL02 | 02-04-02-BREL02 | Trabajo parada: Bomba Relaves 02 StBy | 12.8 | PAHELE01 | MEC | 4 | No
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-011 | OCP-CON1-MBOL02 | 02-02-02-MBOL02 | Trabajo parada: Molino Bolas 26x40.5 L2 | 14.4 | PARMEC01 | ELE | 5 | Si
SD-2026-02-MAJ | WP-SD-2026-02-MAJ-012 | OCP-CON1-MBOL02 | 02-02-02-MBOL02 | Trabajo parada: Molino Bolas 26x40.5 L2 | 12.5 | PARINS01 | ELE | 2 | No
SD-2026-03-MIN | WP-SD-2026-03-MIN-001 | OCP-CON1-CFRO01 | 02-03-01-CFRO01 | Trabajo parada: Celda Flotacion Rougher 300m3 C1 | 12.4 | PAHINS01 | INS | 2 | Si
SD-2026-03-MIN | WP-SD-2026-03-MIN-002 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 10.9 | PAHELE01 | INS | 5 | Si
SD-2026-03-MIN | WP-SD-2026-03-MIN-003 | OCP-CON1-AGIT01 | 02-03-03-AGIT01 | Trabajo parada: Acondicionador Reactivos 01 | 3.1 | PAHMEC01 | INS | 5 | Si
SD-2026-03-MIN | WP-SD-2026-03-MIN-004 | OCP-CON1-HARV01 | 02-01-04-HARV01 | Trabajo parada: Harnero Vibratorio 01 | 15.2 | PASMEC01 | INS | 4 | No
SD-2026-03-MIN | WP-SD-2026-03-MIN-005 | OCP-CON1-DREA01 | 02-03-03-DREA01 | Trabajo parada: Dosificador Reactivos Colector | 3.9 | PAHELE01 | INS | 4 | Si
SD-2026-03-MIN | WP-SD-2026-03-MIN-006 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 5.6 | PASINS01 | MEC | 3 | No
SD-2026-03-MIN | WP-SD-2026-03-MIN-007 | OCP-CON1-HCIC03 | 02-02-04-HCIC03 | Trabajo parada: Nido Hidrociclones HCI-03 StBy | 13.6 | PARINS01 | MEC | 4 | Si
SD-2026-03-MIN | WP-SD-2026-03-MIN-008 | OCP-CON1-COSE02 | 02-01-02-COSE02 | Trabajo parada: Chancador Cono Secundario HP800 L2 | 15.8 | PASMEC01 | INS | 4 | No
SD-2026-03-MIN | WP-SD-2026-03-MIN-009 | OCP-CON1-CFRO01 | 02-03-01-CFRO01 | Trabajo parada: Celda Flotacion Rougher 300m3 C1 | 3.5 | PAHINS01 | MEC | 4 | Si
SD-2026-03-MIN | WP-SD-2026-03-MIN-010 | OCP-CON1-CFRO03 | 02-03-01-CFRO03 | Trabajo parada: Celda Flotacion Rougher 300m3 C3 | 7.9 | PAHELE01 | MEC | 3 | No
SD-2026-03-MIN | WP-SD-2026-03-MIN-011 | OCP-CON1-CHAN02 | 02-01-01-CHAN02 | Trabajo parada: Chancador Giratorio 60x113 StBy | 13.2 | PASMEC01 | MEC | 3 | No
SD-2026-03-PM | WP-SD-2026-03-PM-001 | OCP-CON1-CFCL02 | 02-03-02-CFCL02 | Trabajo parada: Celda Flotacion Cleaner 160m3 C2 | 2.3 | PAHMEC01 | ELE | 6 | Si
SD-2026-03-PM | WP-SD-2026-03-PM-002 | OCP-CON1-CORR02 | 02-01-04-CORR02 | Trabajo parada: Correa Transportadora CV-002 | 14.2 | PASELE01 | ELE | 5 | Si
SD-2026-03-PM | WP-SD-2026-03-PM-003 | OCP-CON1-HARV03 | 02-01-04-HARV03 | Trabajo parada: Harnero Vibratorio 03 | 3.4 | PASLUB01 | MEC | 6 | No
SD-2026-03-PM | WP-SD-2026-03-PM-004 | OCP-CON1-HCIC01 | 02-02-04-HCIC01 | Trabajo parada: Nido Hidrociclones HCI-01 | 5.8 | PARINS01 | INS | 3 | Si
SD-2026-03-PM | WP-SD-2026-03-PM-005 | OCP-CON1-ESPC02 | 02-04-01-ESPC02 | Trabajo parada: Espesador Concentrado Hi-Rate 25m S | 4 | PAHELE01 | INS | 2 | Si
SD-2026-03-PM | WP-SD-2026-03-PM-006 | OCP-CON1-CFRO02 | 02-03-01-CFRO02 | Trabajo parada: Celda Flotacion Rougher 300m3 C2 | 6.1 | PAHMEC01 | INS | 6 | No
SD-2026-03-PM | WP-SD-2026-03-PM-007 | OCP-CON1-CORR02 | 02-01-04-CORR02 | Trabajo parada: Correa Transportadora CV-002 | 3.9 | PASINS01 | INS | 6 | Si
SD-2026-03-PM | WP-SD-2026-03-PM-008 | OCP-CON1-ANPH01 | 02-05-03-ANPH01 | Trabajo parada: Analizador pH Flotacion | 5.7 | PASINS01 | ELE | 4 | No
SD-2026-03-PM | WP-SD-2026-03-PM-009 | OCP-CON1-BREL01 | 02-04-02-BREL01 | Trabajo parada: Bomba Relaves 01 | 9.7 | PAHELE01 | INS | 3 | Si
SD-2026-03-PM | WP-SD-2026-03-PM-010 | OCP-CON1-BAGP02 | 02-05-03-BAGP02 | Trabajo parada: Bomba Agua Proceso 02 StBy | 11.4 | PASMEC01 | MEC | 2 | Si
SD-2026-04-MIN | WP-SD-2026-04-MIN-001 | OCP-CON1-COSE02 | 02-01-02-COSE02 | Trabajo parada: Chancador Cono Secundario HP800 L2 | 9.2 | PASELE01 | INS | 3 | No
SD-2026-04-MIN | WP-SD-2026-04-MIN-002 | OCP-CON1-FLMT01 | 02-05-03-FLMT01 | Trabajo parada: Flujometro Electromagnetico Pulpa | 11.3 | PASELE01 | INS | 3 | Si
SD-2026-04-MIN | WP-SD-2026-04-MIN-003 | OCP-CON1-HCIC03 | 02-02-04-HCIC03 | Trabajo parada: Nido Hidrociclones HCI-03 StBy | 2 | PARELE01 | ELE | 5 | No
SD-2026-04-MIN | WP-SD-2026-04-MIN-004 | OCP-CON1-AGIT02 | 02-03-03-AGIT02 | Trabajo parada: Acondicionador Reactivos 02 | 4.1 | PAHINS01 | ELE | 6 | No
SD-2026-04-MIN | WP-SD-2026-04-MIN-005 | OCP-CON1-SECA01 | 02-05-02-SECA01 | Trabajo parada: Secador Rotatorio Concentrado | 14.3 | PASELE01 | INS | 3 | No
SD-2026-04-MIN | WP-SD-2026-04-MIN-006 | OCP-CON1-COSE01 | 02-01-02-COSE01 | Trabajo parada: Chancador Cono Secundario HP800 L1 | 12 | PASINS01 | ELE | 4 | Si
SD-2026-04-MIN | WP-SD-2026-04-MIN-007 | OCP-CON1-BOMB03 | 02-02-03-BOMB03 | Trabajo parada: Bomba Pulpa Descarga SAG 03 StBy | 11.9 | PARMEC01 | MEC | 5 | No
SD-2026-04-MIN | WP-SD-2026-04-MIN-008 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 6.4 | PARELE01 | INS | 5 | Si
SD-2026-04-MIN | WP-SD-2026-04-MIN-009 | OCP-CON1-ANPH01 | 02-05-03-ANPH01 | Trabajo parada: Analizador pH Flotacion | 2.3 | PASMEC01 | INS | 5 | Si
SD-2026-04-MIN | WP-SD-2026-04-MIN-010 | OCP-CON1-DENS01 | 02-05-03-DENS01 | Trabajo parada: Densimetro Nuclear Molienda | 6.6 | PASMEC01 | MEC | 4 | No
SD-2026-04-MIN | WP-SD-2026-04-MIN-011 | OCP-CON1-CHAN02 | 02-01-01-CHAN02 | Trabajo parada: Chancador Giratorio 60x113 StBy | 4.7 | PASLUB01 | MEC | 6 | No
SD-2026-04-PM | WP-SD-2026-04-PM-001 | OCP-CON1-FLMT01 | 02-05-03-FLMT01 | Trabajo parada: Flujometro Electromagnetico Pulpa | 5.2 | PASELE01 | MEC | 5 | No
SD-2026-04-PM | WP-SD-2026-04-PM-002 | OCP-CON1-COMP02 | 02-05-03-COMP02 | Trabajo parada: Compresor Aire Planta 02 StBy | 12.3 | PASLUB01 | ELE | 3 | No
SD-2026-04-PM | WP-SD-2026-04-PM-003 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 12 | PAHELE01 | ELE | 3 | No
SD-2026-04-PM | WP-SD-2026-04-PM-004 | OCP-CON1-HARV01 | 02-01-04-HARV01 | Trabajo parada: Harnero Vibratorio 01 | 14.7 | PASLUB01 | MEC | 3 | No
SD-2026-04-PM | WP-SD-2026-04-PM-005 | OCP-CON1-COSE02 | 02-01-02-COSE02 | Trabajo parada: Chancador Cono Secundario HP800 L2 | 5.9 | PASINS01 | MEC | 5 | Si
SD-2026-04-PM | WP-SD-2026-04-PM-006 | OCP-CON1-CFRO01 | 02-03-01-CFRO01 | Trabajo parada: Celda Flotacion Rougher 300m3 C1 | 8.7 | PAHELE01 | MEC | 2 | Si
SD-2026-04-PM | WP-SD-2026-04-PM-007 | OCP-CON1-BAGP01 | 02-05-03-BAGP01 | Trabajo parada: Bomba Agua Proceso 01 | 4.3 | PASLUB01 | INS | 5 | Si
SD-2026-04-PM | WP-SD-2026-04-PM-008 | OCP-CON1-SECA01 | 02-05-02-SECA01 | Trabajo parada: Secador Rotatorio Concentrado | 14.2 | PASMEC01 | MEC | 6 | No
SD-2026-04-PM | WP-SD-2026-04-PM-009 | OCP-CON1-HARV01 | 02-01-04-HARV01 | Trabajo parada: Harnero Vibratorio 01 | 9.2 | PASINS01 | ELE | 2 | No
SD-2026-04-PM | WP-SD-2026-04-PM-010 | OCP-CON1-COSE01 | 02-01-02-COSE01 | Trabajo parada: Chancador Cono Secundario HP800 L1 | 7.9 | PASINS01 | MEC | 2 | Si
SD-2026-04-PM | WP-SD-2026-04-PM-011 | OCP-CON1-CHAN02 | 02-01-01-CHAN02 | Trabajo parada: Chancador Giratorio 60x113 StBy | 6.1 | PASMEC01 | ELE | 4 | Si
SD-2026-04-PM | WP-SD-2026-04-PM-012 | OCP-CON1-HARV01 | 02-01-04-HARV01 | Trabajo parada: Harnero Vibratorio 01 | 4.5 | PASINS01 | INS | 6 | Si
SD-2026-04-PM | WP-SD-2026-04-PM-013 | OCP-CON1-ALIM02 | 02-01-01-ALIM02 | Trabajo parada: Alimentador Apron 02 | 9.4 | PASLUB01 | ELE | 5 | Si
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-001 | OCP-CON1-MBOL03 | 02-02-02-MBOL03 | Trabajo parada: Molino Bolas 26x40.5 L3 | 8.6 | PARMEC01 | ELE | 4 | Si
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-002 | OCP-CON1-FILT02 | 02-05-01-FILT02 | Trabajo parada: Filtro Prensa Concentrado FP-02 | 12.6 | PASMEC01 | MEC | 4 | Si
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-003 | OCP-CON1-CHAN02 | 02-01-01-CHAN02 | Trabajo parada: Chancador Giratorio 60x113 StBy | 15.2 | PASMEC01 | ELE | 3 | Si
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-004 | OCP-CON1-BOMB02 | 02-02-03-BOMB02 | Trabajo parada: Bomba Pulpa Descarga SAG 02 | 9.8 | PARINS01 | ELE | 4 | No
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-005 | OCP-CON1-COTE01 | 02-01-03-COTE01 | Trabajo parada: Chancador Cono Terciario HP500 L1 | 12.5 | PASINS01 | MEC | 3 | No
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-006 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 5.6 | PAHELE01 | ELE | 6 | No
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-007 | OCP-CON1-BAGP02 | 02-05-03-BAGP02 | Trabajo parada: Bomba Agua Proceso 02 StBy | 10.9 | PASINS01 | INS | 5 | No
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-008 | OCP-CON1-CORR02 | 02-01-04-CORR02 | Trabajo parada: Correa Transportadora CV-002 | 10.1 | PASMEC01 | INS | 4 | No
SD-2026-05-MAJ | WP-SD-2026-05-MAJ-009 | OCP-CON1-CFRO04 | 02-03-01-CFRO04 | Trabajo parada: Celda Flotacion Rougher 300m3 C4 | 3.9 | PAHELE01 | MEC | 3 | No
SD-2026-06-MIN | WP-SD-2026-06-MIN-001 | OCP-CON1-COMP01 | 02-05-03-COMP01 | Trabajo parada: Compresor Aire Planta 01 | 13.3 | PASELE01 | ELE | 5 | Si
SD-2026-06-MIN | WP-SD-2026-06-MIN-002 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 13.9 | PASINS01 | INS | 6 | No
SD-2026-06-MIN | WP-SD-2026-06-MIN-003 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 15.2 | PARELE01 | INS | 2 | No
SD-2026-06-MIN | WP-SD-2026-06-MIN-004 | OCP-CON1-CFRO04 | 02-03-01-CFRO04 | Trabajo parada: Celda Flotacion Rougher 300m3 C4 | 9.1 | PAHINS01 | MEC | 4 | Si
SD-2026-06-MIN | WP-SD-2026-06-MIN-005 | OCP-CON1-CORR05 | 02-05-02-CORR05 | Trabajo parada: Correa Transportadora CV-051 | 6.7 | PASLUB01 | INS | 2 | Si
SD-2026-06-MIN | WP-SD-2026-06-MIN-006 | OCP-CON1-ALIM02 | 02-01-01-ALIM02 | Trabajo parada: Alimentador Apron 02 | 5.1 | PASMEC01 | ELE | 4 | No
SD-2026-06-MIN | WP-SD-2026-06-MIN-007 | OCP-CON1-DREA03 | 02-03-03-DREA03 | Trabajo parada: Dosificador Cal/pH | 11.5 | PAHMEC01 | ELE | 4 | Si
SD-2026-06-MIN | WP-SD-2026-06-MIN-008 | OCP-CON1-ALIM02 | 02-01-01-ALIM02 | Trabajo parada: Alimentador Apron 02 | 15.4 | PASELE01 | MEC | 5 | Si
SD-2026-06-MIN | WP-SD-2026-06-MIN-009 | OCP-CON1-HCIC03 | 02-02-04-HCIC03 | Trabajo parada: Nido Hidrociclones HCI-03 StBy | 14.1 | PARELE01 | MEC | 5 | No
SD-2026-06-MIN | WP-SD-2026-06-MIN-010 | OCP-CON1-HCIC03 | 02-02-04-HCIC03 | Trabajo parada: Nido Hidrociclones HCI-03 StBy | 6.4 | PARELE01 | MEC | 4 | Si
SD-2026-06-MIN | WP-SD-2026-06-MIN-011 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 3.8 | PARELE01 | MEC | 5 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-001 | OCP-CON1-ANPH01 | 02-05-03-ANPH01 | Trabajo parada: Analizador pH Flotacion | 3.6 | PASLUB01 | INS | 6 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-002 | OCP-CON1-DENS01 | 02-05-03-DENS01 | Trabajo parada: Densimetro Nuclear Molienda | 4.3 | PASLUB01 | ELE | 5 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-003 | OCP-CON1-DREA02 | 02-03-03-DREA02 | Trabajo parada: Dosificador Reactivos Espumante | 15.2 | PAHMEC01 | INS | 3 | No
SD-2026-06-PM | WP-SD-2026-06-PM-004 | OCP-CON1-CFCL01 | 02-03-02-CFCL01 | Trabajo parada: Celda Flotacion Cleaner 160m3 C1 | 12.2 | PAHELE01 | ELE | 4 | No
SD-2026-06-PM | WP-SD-2026-06-PM-005 | OCP-CON1-COSE02 | 02-01-02-COSE02 | Trabajo parada: Chancador Cono Secundario HP800 L2 | 7.7 | PASMEC01 | MEC | 3 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-006 | OCP-CON1-FILT03 | 02-05-01-FILT03 | Trabajo parada: Filtro Prensa Concentrado FP-03 StB | 11.1 | PASELE01 | MEC | 5 | No
SD-2026-06-PM | WP-SD-2026-06-PM-007 | OCP-CON1-MSAG02 | 02-02-01-MSAG02 | Trabajo parada: Molino SAG 40x22 L2 | 8.8 | PARMEC01 | ELE | 5 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-008 | OCP-CON1-HCIC02 | 02-02-04-HCIC02 | Trabajo parada: Nido Hidrociclones HCI-02 | 4.5 | PARELE01 | MEC | 3 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-009 | OCP-CON1-MBOL02 | 02-02-02-MBOL02 | Trabajo parada: Molino Bolas 26x40.5 L2 | 5.4 | PARMEC01 | MEC | 3 | No
SD-2026-06-PM | WP-SD-2026-06-PM-010 | OCP-CON1-CFRO02 | 02-03-01-CFRO02 | Trabajo parada: Celda Flotacion Rougher 300m3 C2 | 10.5 | PAHELE01 | MEC | 6 | No
SD-2026-06-PM | WP-SD-2026-06-PM-011 | OCP-CON1-COSE01 | 02-01-02-COSE01 | Trabajo parada: Chancador Cono Secundario HP800 L1 | 10.8 | PASELE01 | MEC | 2 | Si
SD-2026-06-PM | WP-SD-2026-06-PM-012 | OCP-CON1-CORR02 | 02-01-04-CORR02 | Trabajo parada: Correa Transportadora CV-002 | 7.8 | PASINS01 | INS | 3 | No
SD-2026-06-PM | WP-SD-2026-06-PM-013 | OCP-CON1-ESPR01 | 02-04-02-ESPR01 | Trabajo parada: Espesador Relaves 45m | 10.2 | PAHELE01 | MEC | 5 | No
SD-2026-07-MIN | WP-SD-2026-07-MIN-001 | OCP-CON1-AGIT01 | 02-03-03-AGIT01 | Trabajo parada: Acondicionador Reactivos 01 | 15.1 | PAHINS01 | ELE | 5 | No
SD-2026-07-MIN | WP-SD-2026-07-MIN-002 | OCP-CON1-CHAN01 | 02-01-01-CHAN01 | Trabajo parada: Chancador Giratorio 60x113 | 4 | PASELE01 | ELE | 3 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-003 | OCP-CON1-CORR01 | 02-01-04-CORR01 | Trabajo parada: Correa Transportadora CV-001 | 11.5 | PASINS01 | INS | 6 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-004 | OCP-CON1-DREA02 | 02-03-03-DREA02 | Trabajo parada: Dosificador Reactivos Espumante | 7 | PAHINS01 | MEC | 6 | No
SD-2026-07-MIN | WP-SD-2026-07-MIN-005 | OCP-CON1-BOMB02 | 02-02-03-BOMB02 | Trabajo parada: Bomba Pulpa Descarga SAG 02 | 6.1 | PARINS01 | ELE | 2 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-006 | OCP-CON1-HCIC02 | 02-02-04-HCIC02 | Trabajo parada: Nido Hidrociclones HCI-02 | 2.3 | PARMEC01 | INS | 6 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-007 | OCP-CON1-BOMB02 | 02-02-03-BOMB02 | Trabajo parada: Bomba Pulpa Descarga SAG 02 | 12.5 | PARINS01 | INS | 6 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-008 | OCP-CON1-DREA01 | 02-03-03-DREA01 | Trabajo parada: Dosificador Reactivos Colector | 11.6 | PAHMEC01 | INS | 3 | No
SD-2026-07-MIN | WP-SD-2026-07-MIN-009 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 10.7 | PASMEC01 | INS | 6 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-010 | OCP-CON1-MSAG02 | 02-02-01-MSAG02 | Trabajo parada: Molino SAG 40x22 L2 | 15 | PARELE01 | MEC | 6 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-011 | OCP-CON1-CORR04 | 02-05-02-CORR04 | Trabajo parada: Correa Transportadora CV-050 | 12.7 | PASLUB01 | INS | 5 | Si
SD-2026-07-MIN | WP-SD-2026-07-MIN-012 | OCP-CON1-ALIM02 | 02-01-01-ALIM02 | Trabajo parada: Alimentador Apron 02 | 8 | PASLUB01 | MEC | 4 | No
SD-2026-07-MIN | WP-SD-2026-07-MIN-013 | OCP-CON1-CFRO01 | 02-03-01-CFRO01 | Trabajo parada: Celda Flotacion Rougher 300m3 C1 | 16 | PAHMEC01 | ELE | 2 | No
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-001 | OCP-CON1-MBOL03 | 02-02-02-MBOL03 | Trabajo parada: Molino Bolas 26x40.5 L3 | 12.6 | PARELE01 | INS | 2 | Si
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-002 | OCP-CON1-DENS01 | 02-05-03-DENS01 | Trabajo parada: Densimetro Nuclear Molienda | 14.9 | PASELE01 | INS | 2 | Si
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-003 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 6 | PARELE01 | INS | 6 | Si
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-004 | OCP-CON1-CFCL01 | 02-03-02-CFCL01 | Trabajo parada: Celda Flotacion Cleaner 160m3 C1 | 5.9 | PAHINS01 | INS | 2 | No
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-005 | OCP-CON1-BOMB04 | 02-02-03-BOMB04 | Trabajo parada: Bomba Pulpa Alimentacion Bolas 01 | 10.8 | PARMEC01 | INS | 3 | Si
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-006 | OCP-CON1-COMP01 | 02-05-03-COMP01 | Trabajo parada: Compresor Aire Planta 01 | 11.7 | PASELE01 | MEC | 2 | No
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-007 | OCP-CON1-AGIT01 | 02-03-03-AGIT01 | Trabajo parada: Acondicionador Reactivos 01 | 3.4 | PAHELE01 | ELE | 3 | Si
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-008 | OCP-CON1-BREL01 | 02-04-02-BREL01 | Trabajo parada: Bomba Relaves 01 | 14.5 | PAHMEC01 | ELE | 6 | Si
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-009 | OCP-CON1-ALIM01 | 02-01-01-ALIM01 | Trabajo parada: Alimentador Apron 01 | 8.5 | PASMEC01 | ELE | 2 | No
SD-2026-08-MAJ | WP-SD-2026-08-MAJ-010 | OCP-CON1-DREA03 | 02-03-03-DREA03 | Trabajo parada: Dosificador Cal/pH | 9.5 | PAHELE01 | ELE | 6 | No
SD-2026-09-MIN | WP-SD-2026-09-MIN-001 | OCP-CON1-DENS01 | 02-05-03-DENS01 | Trabajo parada: Densimetro Nuclear Molienda | 3.7 | PASELE01 | ELE | 3 | Si
SD-2026-09-MIN | WP-SD-2026-09-MIN-002 | OCP-CON1-MBOL02 | 02-02-02-MBOL02 | Trabajo parada: Molino Bolas 26x40.5 L2 | 12.7 | PARELE01 | ELE | 6 | Si
SD-2026-09-MIN | WP-SD-2026-09-MIN-003 | OCP-CON1-BREL01 | 02-04-02-BREL01 | Trabajo parada: Bomba Relaves 01 | 11.4 | PAHINS01 | ELE | 4 | No
SD-2026-09-MIN | WP-SD-2026-09-MIN-004 | OCP-CON1-CORR04 | 02-05-02-CORR04 | Trabajo parada: Correa Transportadora CV-050 | 15.3 | PASELE01 | INS | 3 | No
SD-2026-09-MIN | WP-SD-2026-09-MIN-005 | OCP-CON1-FLMT01 | 02-05-03-FLMT01 | Trabajo parada: Flujometro Electromagnetico Pulpa | 2.6 | PASINS01 | MEC | 6 | Si
SD-2026-09-MIN | WP-SD-2026-09-MIN-006 | OCP-CON1-COSE01 | 02-01-02-COSE01 | Trabajo parada: Chancador Cono Secundario HP800 L1 | 5.6 | PASELE01 | INS | 2 | Si
SD-2026-09-MIN | WP-SD-2026-09-MIN-007 | OCP-CON1-BAGP01 | 02-05-03-BAGP01 | Trabajo parada: Bomba Agua Proceso 01 | 15.1 | PASINS01 | MEC | 6 | Si
SD-2026-09-MIN | WP-SD-2026-09-MIN-008 | OCP-CON1-HCIC02 | 02-02-04-HCIC02 | Trabajo parada: Nido Hidrociclones HCI-02 | 7.3 | PARELE01 | INS | 6 | No
SD-2026-09-MIN | WP-SD-2026-09-MIN-009 | OCP-CON1-CORR01 | 02-01-04-CORR01 | Trabajo parada: Correa Transportadora CV-001 | 9.9 | PASLUB01 | ELE | 5 | No
SD-2026-09-MIN | WP-SD-2026-09-MIN-010 | OCP-CON1-BAGP01 | 02-05-03-BAGP01 | Trabajo parada: Bomba Agua Proceso 01 | 2.7 | PASINS01 | ELE | 4 | No
SD-2026-09-MIN | WP-SD-2026-09-MIN-011 | OCP-CON1-FILT01 | 02-05-01-FILT01 | Trabajo parada: Filtro Prensa Concentrado FP-01 | 2.9 | PASELE01 | MEC | 5 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-001 | OCP-CON1-CORR05 | 02-05-02-CORR05 | Trabajo parada: Correa Transportadora CV-051 | 9.5 | PASMEC01 | INS | 6 | No
SD-2026-09-PM | WP-SD-2026-09-PM-002 | OCP-CON1-CFCL02 | 02-03-02-CFCL02 | Trabajo parada: Celda Flotacion Cleaner 160m3 C2 | 3 | PAHINS01 | MEC | 4 | No
SD-2026-09-PM | WP-SD-2026-09-PM-003 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 13.1 | PAHMEC01 | ELE | 5 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-004 | OCP-CON1-SECA01 | 02-05-02-SECA01 | Trabajo parada: Secador Rotatorio Concentrado | 4.2 | PASINS01 | ELE | 5 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-005 | OCP-CON1-VIBM01 | 02-05-03-VIBM01 | Trabajo parada: Monitor Vibracion Molinos | 13.4 | PASELE01 | MEC | 2 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-006 | OCP-CON1-BREL01 | 02-04-02-BREL01 | Trabajo parada: Bomba Relaves 01 | 14.6 | PAHELE01 | ELE | 2 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-007 | OCP-CON1-MSAG02 | 02-02-01-MSAG02 | Trabajo parada: Molino SAG 40x22 L2 | 10 | PARMEC01 | MEC | 4 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-008 | OCP-CON1-COMP02 | 02-05-03-COMP02 | Trabajo parada: Compresor Aire Planta 02 StBy | 10.5 | PASELE01 | ELE | 6 | Si
SD-2026-09-PM | WP-SD-2026-09-PM-009 | OCP-CON1-CORR05 | 02-05-02-CORR05 | Trabajo parada: Correa Transportadora CV-051 | 8.7 | PASINS01 | ELE | 4 | No
SD-2026-09-PM | WP-SD-2026-09-PM-010 | OCP-CON1-CORR05 | 02-05-02-CORR05 | Trabajo parada: Correa Transportadora CV-051 | 12.4 | PASINS01 | ELE | 5 | No
SD-2026-09-PM | WP-SD-2026-09-PM-011 | OCP-CON1-BAGP02 | 02-05-03-BAGP02 | Trabajo parada: Bomba Agua Proceso 02 StBy | 15.8 | PASMEC01 | MEC | 3 | Si
SD-2026-10-MIN | WP-SD-2026-10-MIN-001 | OCP-CON1-BOMB02 | 02-02-03-BOMB02 | Trabajo parada: Bomba Pulpa Descarga SAG 02 | 13.4 | PARINS01 | MEC | 2 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-002 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 14.9 | PARINS01 | ELE | 5 | Si
SD-2026-10-MIN | WP-SD-2026-10-MIN-003 | OCP-CON1-ESPR01 | 02-04-02-ESPR01 | Trabajo parada: Espesador Relaves 45m | 12.6 | PAHINS01 | ELE | 5 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-004 | OCP-CON1-ESPR01 | 02-04-02-ESPR01 | Trabajo parada: Espesador Relaves 45m | 6.1 | PAHMEC01 | MEC | 2 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-005 | OCP-CON1-CORR01 | 02-01-04-CORR01 | Trabajo parada: Correa Transportadora CV-001 | 8.9 | PASMEC01 | ELE | 4 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-006 | OCP-CON1-ANPH01 | 02-05-03-ANPH01 | Trabajo parada: Analizador pH Flotacion | 3.5 | PASELE01 | ELE | 2 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-007 | OCP-CON1-HARV02 | 02-01-04-HARV02 | Trabajo parada: Harnero Vibratorio 02 | 4 | PASELE01 | ELE | 3 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-008 | OCP-CON1-BOMB01 | 02-02-03-BOMB01 | Trabajo parada: Bomba Pulpa Descarga SAG 01 | 12.5 | PARMEC01 | MEC | 3 | Si
SD-2026-10-MIN | WP-SD-2026-10-MIN-009 | OCP-CON1-HCIC02 | 02-02-04-HCIC02 | Trabajo parada: Nido Hidrociclones HCI-02 | 7 | PARMEC01 | MEC | 2 | Si
SD-2026-10-MIN | WP-SD-2026-10-MIN-010 | OCP-CON1-HARV03 | 02-01-04-HARV03 | Trabajo parada: Harnero Vibratorio 03 | 3.7 | PASINS01 | ELE | 4 | Si
SD-2026-10-MIN | WP-SD-2026-10-MIN-011 | OCP-CON1-HARV03 | 02-01-04-HARV03 | Trabajo parada: Harnero Vibratorio 03 | 13.8 | PASELE01 | INS | 6 | Si
SD-2026-10-MIN | WP-SD-2026-10-MIN-012 | OCP-CON1-COMP02 | 02-05-03-COMP02 | Trabajo parada: Compresor Aire Planta 02 StBy | 13.1 | PASLUB01 | INS | 2 | No
SD-2026-10-MIN | WP-SD-2026-10-MIN-013 | OCP-CON1-BREL02 | 02-04-02-BREL02 | Trabajo parada: Bomba Relaves 02 StBy | 2.3 | PAHELE01 | INS | 2 | No
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-001 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 4.6 | PASMEC01 | MEC | 3 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-002 | OCP-CON1-BREL02 | 02-04-02-BREL02 | Trabajo parada: Bomba Relaves 02 StBy | 8.2 | PAHINS01 | MEC | 5 | No
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-003 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 13.7 | PASLUB01 | ELE | 3 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-004 | OCP-CON1-CORR01 | 02-01-04-CORR01 | Trabajo parada: Correa Transportadora CV-001 | 8.8 | PASLUB01 | ELE | 6 | No
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-005 | OCP-CON1-COTE02 | 02-01-03-COTE02 | Trabajo parada: Chancador Cono Terciario HP500 L2 | 13.7 | PASELE01 | ELE | 6 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-006 | OCP-CON1-HCIC01 | 02-02-04-HCIC01 | Trabajo parada: Nido Hidrociclones HCI-01 | 8.3 | PARELE01 | INS | 2 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-007 | OCP-CON1-COMP01 | 02-05-03-COMP01 | Trabajo parada: Compresor Aire Planta 01 | 8.7 | PASLUB01 | MEC | 6 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-008 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 10.1 | PAHMEC01 | ELE | 5 | No
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-009 | OCP-CON1-VIBM01 | 02-05-03-VIBM01 | Trabajo parada: Monitor Vibracion Molinos | 10.4 | PASELE01 | ELE | 4 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-010 | OCP-CON1-CHAN01 | 02-01-01-CHAN01 | Trabajo parada: Chancador Giratorio 60x113 | 10.8 | PASELE01 | INS | 6 | Si
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-011 | OCP-CON1-ALIM01 | 02-01-01-ALIM01 | Trabajo parada: Alimentador Apron 01 | 13.4 | PASINS01 | INS | 6 | No
SD-2026-11-MAJ | WP-SD-2026-11-MAJ-012 | OCP-CON1-FILT02 | 02-05-01-FILT02 | Trabajo parada: Filtro Prensa Concentrado FP-02 | 8.1 | PASINS01 | ELE | 6 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-001 | OCP-CON1-MSAG02 | 02-02-01-MSAG02 | Trabajo parada: Molino SAG 40x22 L2 | 6.2 | PARINS01 | ELE | 3 | Si
SD-2026-12-MIN | WP-SD-2026-12-MIN-002 | OCP-CON1-HARV01 | 02-01-04-HARV01 | Trabajo parada: Harnero Vibratorio 01 | 9.5 | PASELE01 | ELE | 3 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-003 | OCP-CON1-MBOL02 | 02-02-02-MBOL02 | Trabajo parada: Molino Bolas 26x40.5 L2 | 6.5 | PARINS01 | ELE | 4 | Si
SD-2026-12-MIN | WP-SD-2026-12-MIN-004 | OCP-CON1-ALIM02 | 02-01-01-ALIM02 | Trabajo parada: Alimentador Apron 02 | 8.9 | PASMEC01 | ELE | 5 | Si
SD-2026-12-MIN | WP-SD-2026-12-MIN-005 | OCP-CON1-BOMB05 | 02-02-03-BOMB05 | Trabajo parada: Bomba Pulpa Alimentacion Bolas 02 | 3.9 | PARINS01 | INS | 4 | Si
SD-2026-12-MIN | WP-SD-2026-12-MIN-006 | OCP-CON1-FLMT01 | 02-05-03-FLMT01 | Trabajo parada: Flujometro Electromagnetico Pulpa | 11.3 | PASMEC01 | INS | 6 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-007 | OCP-CON1-DREA03 | 02-03-03-DREA03 | Trabajo parada: Dosificador Cal/pH | 12.8 | PAHMEC01 | INS | 5 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-008 | OCP-CON1-ESPC01 | 02-04-01-ESPC01 | Trabajo parada: Espesador Concentrado Hi-Rate 25m | 10.2 | PAHELE01 | MEC | 4 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-009 | OCP-CON1-BOMB03 | 02-02-03-BOMB03 | Trabajo parada: Bomba Pulpa Descarga SAG 03 StBy | 6.3 | PARINS01 | INS | 3 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-010 | OCP-CON1-DREA01 | 02-03-03-DREA01 | Trabajo parada: Dosificador Reactivos Colector | 7.9 | PAHELE01 | ELE | 6 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-011 | OCP-CON1-MBOL02 | 02-02-02-MBOL02 | Trabajo parada: Molino Bolas 26x40.5 L2 | 11.3 | PARINS01 | MEC | 6 | No
SD-2026-12-MIN | WP-SD-2026-12-MIN-012 | OCP-CON1-VIBM01 | 02-05-03-VIBM01 | Trabajo parada: Monitor Vibracion Molinos | 3 | PASLUB01 | ELE | 5 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-001 | OCP-CON1-FLMT01 | 02-05-03-FLMT01 | Trabajo parada: Flujometro Electromagnetico Pulpa | 4.5 | PASINS01 | INS | 4 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-002 | OCP-CON1-CFRO04 | 02-03-01-CFRO04 | Trabajo parada: Celda Flotacion Rougher 300m3 C4 | 13.4 | PAHELE01 | INS | 4 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-003 | OCP-CON1-CFSC01 | 02-03-02-CFSC01 | Trabajo parada: Celda Flotacion Scavenger 300m3 C1 | 13 | PAHMEC01 | INS | 3 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-004 | OCP-CON1-BAGP02 | 02-05-03-BAGP02 | Trabajo parada: Bomba Agua Proceso 02 StBy | 15.3 | PASELE01 | INS | 4 | No
SD-2026-12-PM | WP-SD-2026-12-PM-005 | OCP-CON1-CORR01 | 02-01-04-CORR01 | Trabajo parada: Correa Transportadora CV-001 | 15 | PASLUB01 | MEC | 5 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-006 | OCP-CON1-BOMB02 | 02-02-03-BOMB02 | Trabajo parada: Bomba Pulpa Descarga SAG 02 | 8.5 | PARELE01 | ELE | 2 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-007 | OCP-CON1-ALIM01 | 02-01-01-ALIM01 | Trabajo parada: Alimentador Apron 01 | 6 | PASINS01 | MEC | 2 | Si
SD-2026-12-PM | WP-SD-2026-12-PM-008 | OCP-CON1-CFSC02 | 02-03-02-CFSC02 | Trabajo parada: Celda Flotacion Scavenger 300m3 C2 | 12.7 | PAHELE01 | MEC | 2 | No
SD-2026-12-PM | WP-SD-2026-12-PM-009 | OCP-CON1-DREA02 | 02-03-03-DREA02 | Trabajo parada: Dosificador Reactivos Espumante | 12.1 | PAHINS01 | ELE | 2 | Si