## Instructions
AI-Powered Asset Management — Required Documentation
PURPOSE
This workbook lists all documents required from the client to fully customize
the AI-Powered Asset Management and Maintenance Solution.
HOW TO USE
1. Go to the 'Document Tracker' sheet — this is the main checklist
2. For each document item, update the STATUS column:
- Pending: Not yet collected
- In Progress: Being gathered by client
- Received: Delivered to VSC
- N/A: Not applicable for this engagement
3. Fill in Received Date when documents arrive
4. Fill in Responsible (Client) — who will provide this document
5. Use Quality (1-5) to rate data quality once received
6. Add Notes for any issues, alternatives, or clarifications
PRIORITY LEVELS
CRITICAL (Red) — Week 1-2: Absolute minimum to start development
IMPORTANT (Yellow) — Week 3-4: Required to complete functionalities
DESIRABLE (Green) — Week 5-6: Enriches the solution
DELIVERY TIMELINE
Week 1-2: Equipment hierarchy, Work orders, Spare parts, Inventory, Backlog
Week 3-4: Technical manuals, PM plans, Workforce, Shutdowns, Production plan
Week 5-6: FMEA, Photographs, Condition monitoring, Costs, Workflows
QUALITY SCALE
1 = Unusable (major errors, missing key fields)
2 = Poor (many gaps, needs significant cleaning)
3 = Acceptable (some gaps, usable with effort)
4 = Good (minor gaps, mostly clean)
5 = Excellent (complete, clean, ready to use)

## Document Tracker
ID | Category | Document / Item | Specific Content Required | Expected Format | SAP Transaction | Priority | Delivery Target | Status | Received Date | Responsible (Client) | Quality (1-5) | File Name(s) | Notes
DOC-01 | Work Management Workflow Documentation |  |  |  |  | DESIRABLE | Week 5-6
01.01 | Work Management Workflow Documentation | AS-IS Workflow Map | Current work request process: how inspectors/operators submit requests (email, verbal, SAP, etc.), current approval chain and decision points, information flow between production/maintenance/planning, average times per stage, identified friction points | PowerPoint / Visio / Word |  | DESIRABLE | Week 5-6 | Pending
01.02 | Work Management Workflow Documentation | Work Request Standard | Templates currently in use, required information fields, approval authorities by work type, priority classification criteria | Word / PDF |  | DESIRABLE | Week 5-6 | Pending
01.03 | Work Management Workflow Documentation | Planning Process Documentation | How planner receives and processes requests, information gathering steps (materials, resources, timing), communication protocols with warehouse/supervisors/production, scheduling rules and constraints | Word / PDF |  | DESIRABLE | Week 5-6 | Pending
01.04 | Work Management Workflow Documentation | Work Management Framework & SAP Configuration Blueprint | Business Process Maps for Work Management: Identification & Prioritization, Planning, Scheduling, Execution, Monitoring/Controlling/Closing. SAP PM rules and Master Data configuration | PowerPoint / Visio / Word |  | DESIRABLE | Week 5-6 | Pending
DOC-02 | Equipment Hierarchy & Master Data |  |  |  |  | CRITICAL | Week 1-2
02.01 | Equipment Hierarchy & Master Data | Complete SAP Hierarchical Structure | Full hierarchy: Plant > Area > System > Equipment > Component. Asset Register with Equipment Make, Model, Component TAGs | CSV / Excel export from SAP | IE01/IH01 | CRITICAL | Week 1-2 | Pending
02.02 | Equipment Hierarchy & Master Data | Pilot Equipment TAGs | TAGs of the 1-2 selected pilot equipment and their complete sub-hierarchy | CSV / Excel |  | CRITICAL | Week 1-2 | Pending
02.03 | Equipment Hierarchy & Master Data | Criticality Classification | Criticality rating for equipment (e.g., AA, A+, C, D) as currently defined | CSV / Excel export from SAP | IH06/IH08 | CRITICAL | Week 1-2 | Pending
02.04 | Equipment Hierarchy & Master Data | Physical Location Mapping | Physical location identifiers for each equipment in the hierarchy | CSV / Excel export from SAP |  | CRITICAL | Week 1-2 | Pending
DOC-03 | Work Orders History |  |  |  |  | CRITICAL | Week 1-2
03.01 | Work Orders History | Work Orders Export (min. 12 months) | Work order number, Equipment TAG, Type (PM01 Inspection / PM02 Preventive / PM03 Corrective), Execution date, Duration in man-hours, Equipment/Component worked on, Problem description, Materials consumed, Final status (completed/pending/rescheduled), Reason for postponement | SAP export IW38/IW39 | IW38/IW39 | CRITICAL | Week 1-2 | Pending
03.02 | Work Orders History | Work Order Notifications | Associated notifications with cause codes, damage codes, and activity types | SAP export IW28/IW29 | IW28/IW29 | CRITICAL | Week 1-2 | Pending
DOC-04 | Spare Parts Catalog (BOM) |  |  |  |  | CRITICAL | Week 1-2
04.01 | Spare Parts Catalog (BOM) | Bill of Materials per Pilot Equipment | SAP spare part code, Spare part description, Common description, Applicable equipment, Supplier lead time, Criticality | Excel / CSV from SAP | CS12/IB01 | CRITICAL | Week 1-2 | Pending
04.02 | Spare Parts Catalog (BOM) | BOM Structure Export | Full multi-level BOM structure showing parent-child relationships for pilot equipment | SAP export IB01/CS12 | CS12/IB01 | CRITICAL | Week 1-2 | Pending
DOC-05 | Current Spare Parts Inventory |  |  |  |  | CRITICAL | Week 1-2
05.01 | Current Spare Parts Inventory | Inventory Levels | SAP code, Available quantity, Warehouse location, Minimum/safety stock levels | Excel / CSV from SAP | MB52/MMBE | CRITICAL | Week 1-2 | Pending
05.02 | Current Spare Parts Inventory | Stock Movement History (12 months) | Consumption history per material code — issues, receipts, adjustments | SAP export MB52/MB51 | MB51 | CRITICAL | Week 1-2 | Pending
DOC-06 | Current Maintenance Backlog |  |  |  |  | CRITICAL | Week 1-2
06.01 | Current Maintenance Backlog | Pending Work Requests (last 3 months) | Work request ID, Assigned priority, Creation date, Current status, Estimated resources, Reason for being pending | Excel / CSV | IW38 (open) | CRITICAL | Week 1-2 | Pending
06.02 | Current Maintenance Backlog | Backlog Age Analysis | Backlog aging breakdown (0-7 days, 7-30 days, 30-90 days, 90+ days) if available | Excel / CSV |  | CRITICAL | Week 1-2 | Pending
DOC-07 | Technical Manuals |  |  |  |  | IMPORTANT | Week 3-4
07.01 | Technical Manuals | Manufacturer O&M Manual | Original Equipment Manufacturer Operation & Maintenance manual for each pilot equipment | PDF |  | IMPORTANT | Week 3-4 | Pending
07.02 | Technical Manuals | P&IDs (Piping & Instrumentation Diagrams) | Process flow diagrams and P&IDs for the pilot area/system | PDF / DWG / Images |  | IMPORTANT | Week 3-4 | Pending
07.03 | Technical Manuals | Technical Specifications / Datasheets | Equipment datasheets with nameplate data, design parameters, operating limits | PDF / Excel |  | IMPORTANT | Week 3-4 | Pending
DOC-08 | Preventive Maintenance Plans |  |  |  |  | IMPORTANT | Week 3-4
08.01 | Preventive Maintenance Plans | PM Plan per Pilot Equipment | Frequency of each PM task, Task list (step-by-step), Associated spare parts, Estimated duration, Required specialties | Excel / CSV from SAP IP10 | IP10/IP16 | IMPORTANT | Week 3-4 | Pending
08.02 | Preventive Maintenance Plans | PM Execution History | Last execution date, Next scheduled date, Compliance rate for each PM task | Excel / CSV from SAP | IP10/IP24 | IMPORTANT | Week 3-4 | Pending
08.03 | Preventive Maintenance Plans | Maintenance Strategy in SAP | Maintenance packages, task lists, and strategy configuration for pilot equipment | SAP export IP16/IA09 | IP16/IA09 | IMPORTANT | Week 3-4 | Pending
DOC-09 | Available Workforce |  |  |  |  | IMPORTANT | Week 3-4
09.01 | Available Workforce | Technician Roster by Specialty | Number of technicians per specialty: Mechanics, Electricians, Instrumentation, Other specialists (welders, riggers, etc.) | Simple Excel |  | IMPORTANT | Week 3-4 | Pending
09.02 | Available Workforce | Work Shifts & Availability | Shift patterns, current availability percentage, overtime rules | Simple Excel |  | IMPORTANT | Week 3-4 | Pending
09.03 | Available Workforce | Contractor Resources | External contractor availability, specialties, response times | Simple Excel |  | IMPORTANT | Week 3-4 | Pending
DOC-10 | Shutdown Calendar |  |  |  |  | IMPORTANT | Week 3-4
10.01 | Shutdown Calendar | Scheduled Shutdowns (next 6 months) | Scheduled shutdown dates, Type (minor 8hrs / major >20hrs), Duration, Affected equipment | Excel / Calendar |  | IMPORTANT | Week 3-4 | Pending
10.02 | Shutdown Calendar | Historical Shutdown Records | Past 12 months of actual shutdowns: planned vs. unplanned, duration, cause | Excel / CSV |  | IMPORTANT | Week 3-4 | Pending
DOC-11 | Production Plan and Schedule |  |  |  |  | IMPORTANT | Week 3-4
11.01 | Production Plan and Schedule | Yearly Production Plan | Annual production targets, throughput rates, seasonal variations | Excel / Calendar |  | IMPORTANT | Week 3-4 | Pending
11.02 | Production Plan and Schedule | Monthly Production Schedule | Basic monthly schedule with production windows and maintenance windows | Excel / Calendar |  | IMPORTANT | Week 3-4 | Pending
11.03 | Production Plan and Schedule | Maintenance Windows & Restrictions | Allowed maintenance windows, known restrictions, production vs. maintenance conflicts | Excel / Calendar |  | IMPORTANT | Week 3-4 | Pending
DOC-12 | Basic FMEA (If Exists) |  |  |  |  | DESIRABLE | Week 5-6
12.01 | Basic FMEA (If Exists) | FMEA / FMECA per Pilot Equipment | Critical components, Identified failure modes, Failure effects, Recommended preventive tasks, RPN scores (if available) | Excel |  | DESIRABLE | Week 5-6 | Pending
12.02 | Basic FMEA (If Exists) | Failure History Analysis | Top 10 failure modes by frequency, failure cause categorization (if available) | Excel / PDF |  | DESIRABLE | Week 5-6 | Pending
DOC-13 | Reference Photographs |  |  |  |  | DESIRABLE | Week 5-6
13.01 | Reference Photographs | Equipment Photographs (5-10 per equipment) | Complete equipment overview, Main components, Typical spare parts, Inspection points, Nameplate | JPG / PNG |  | DESIRABLE | Week 5-6 | Pending
13.02 | Reference Photographs | Area / Layout Photographs | General area layout, access points, safety signage | JPG / PNG |  | DESIRABLE | Week 5-6 | Pending
DOC-14 | Condition Monitoring Data (If Exists) |  |  |  |  | DESIRABLE | Week 5-6
14.01 | Condition Monitoring Data (If Exists) | Vibration Readings | Latest vibration analysis reports for rotating equipment | PDF / Excel |  | DESIRABLE | Week 5-6 | Pending
14.02 | Condition Monitoring Data (If Exists) | Thermography Reports | Recent thermography inspection reports for electrical and mechanical equipment | PDF / Images |  | DESIRABLE | Week 5-6 | Pending
14.03 | Condition Monitoring Data (If Exists) | Active Alarms & Trends | Current active alarms from DCS/SCADA, trend data for key parameters | PDF / Excel / CSV |  | DESIRABLE | Week 5-6 | Pending
DOC-15 | Reference Costs |  |  |  |  | DESIRABLE | Week 5-6
15.01 | Reference Costs | Man-Hour Cost per Specialty | Internal and contractor rates per trade (mechanical, electrical, instrumentation, etc.) | Simple Excel |  | DESIRABLE | Week 5-6 | Pending
15.02 | Reference Costs | Average Material Costs | Average cost of commonly consumed materials and spare parts | Excel / CSV |  | DESIRABLE | Week 5-6 | Pending
15.03 | Reference Costs | Spares Consumption by Equipment | Annual consumption cost breakdown by equipment or system | Excel / CSV from SAP |  | DESIRABLE | Week 5-6 | Pending
15.04 | Reference Costs | Production Loss Cost | Estimated cost per hour of downtime by area/system | Simple Excel |  | DESIRABLE | Week 5-6 | Pending

## Delivery Timeline
Phase | Delivery Target | Priority | Categories | # Documents | What This Enables
Phase 1 | Week 1-2 | CRITICAL | Equipment Hierarchy, Work Orders History, Spare Parts Catalog, Spare Parts Inventory, Maintenance Backlog | 12 | Start prototype of 3 core functionalities: Intelligent capture, Planner assistant, Backlog optimization
Phase 2 | Week 3-4 | IMPORTANT | Technical Manuals, PM Plans, Workforce, Shutdown Calendar, Production Plan & Schedule | 14 | Complete functionalities: Refine algorithms, validate business logic, generate automatic weekly schedule
Phase 3 | Week 5-6 | DESIRABLE | Work Management Workflows, FMEA, Photographs, Condition Monitoring, Reference Costs | 15 | Enrich solution: Predictive failure analysis, PM strategy optimization, advanced insights, optimize UX
TOTAL |  |  |  | 41

## Delivery Format
Preferred Delivery Format
For each document:
Name | Descriptive with date, e.g.: WO_History_SAG_MILL_01_2024-2025.xlsx
Location | Shared folder in Drive/SharePoint organized by category
Contact | Person responsible for that type of information
Notes | Any peculiarities or special considerations
Proposed Folder Structure:
/CLIENT_PROJECT_Data/
/01_Equipment_MasterData/
/02_Work_Orders_History/
/03_Spare_Parts/
/04_Backlog/
/05_Manuals/
/06_Maintenance_Plans/
/07_Resources/
/08_Schedules/
/09_FMEA_RCM/
/10_Photos/
/11_Condition_Monitoring/
/12_Costs/
/13_Processes_Workflows/
Data Quality Notes:
- We don't need perfection in initial data — 'good' data quickly is better than 'perfect' data late.
- We can iterate and improve quality progressively.
- Dummy/synthetic data can be generated if some elements don't exist yet.
- TAGs and names can be anonymized if necessary for confidentiality.